## Test plan
ID | Module | Module Feature | Objectives | Responsiblity | Procedure | Pass/Fail Criteria | Environment | Deadline
1 | Smartphone application | Display history (logs) | Check if history and all data from the user (and only from this said user) are displayed correctly; | Pedro | When requesting the data from the server, check if its only from the person who logged in, and if the time of the request is correctly updated; | Pass: Only the logged in person's history is displayed, and is updated; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
2 |  | Login | Check if the user is able to login with the correct credentials; | Pedro | Check if only the correct set of credentials allow a user profile to be accessed by inputing random login/password combinations (and blank ones too) | Pass: Only the single correct combination of credentials allow the acces to the account; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
3 |  | Insert credits | Check if the user can insert cellphone credits in his account, only after the payment validation (check if he has money); | Pedro | When inserting credits from the app check if: * The credit card is correctly identified; * It only allows to insert credits if there's enough money; * It inserts the credits in the account correctly; * It generates a log in the server; Also the user should try to insert the credits in different times of the day, and in different ocasions eg. right before entering the RU; | Pass: The operation is deemed sucessful and secure, and is registred in the server; The correct amount of credits is added; There's no conflict between operations of different and of the same user; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
4 |  | Access RU | Check if the user can insert the captcha to enter/exit the RU through the turnstiles; | Pedro | When entering/leaving the RU, input captchas in the captcha field and see if the turnstile gets enabled to pass through; | Pass: The turnstile is enabled only for the correct captcha for a set amount of time; The credits are correctly discounted for the correct user; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
5 |  | Board connection | Check if the request to access the RU can only be made when connected in the local network; | Pedro | When entering/leaving the RU, try to do so only while connected in the LAN; | Pass: The user can access the RU only through the LAN; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
6 |  | Display personal info | Check if the user can view his and only his personal info (Name, appCredits, cardCredits, registryNumber); | Pedro | Access the "Personal Info" page and check if the information displayed is only from the logged in person; | Pass: Only the logged in person's personal info is displayed; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
7 |  | Change app pages | Check if the user can access all the app pages avaliable; | Pedro | Change from page to page to see if there's some sort of app bug; | Pass: The user can freely change through every page; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
8 |  | Refresh | Check if the app refreshes when the app is opened, or when the user clicks the "refresh button"; | Pedro | Perform any operation outside the app and enter the app/click the refresh button, and see if the app gets updated; | Pass: The data is correctly updated and the time of the last update is updated; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
9 |  | Server connection | Check if the app can get updated when connected to different networks; | Pedro | Try to refresh/login in the app while connected to different networks (eg. LAN, mobile, anywhere, not connected); | Pass: The data is correctly updated when connected anywhere; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
10 |  | Display number of people inside RU | Check if the user can view the correct number of people inside the restaurant; | Pedro | Make people enter and leave the RU and check if the app can correctly display this info; | Pass: The correct number of people in RU is displayed in a certain timewindow due to refreshing; Fail: Otherwise; | Asus Zenfone 5 | 2017-04-07
11 | Server WEB Application | Login | Check if the user is able to login with the correct credential; | Victor & Lucas | 1. Open the URL of web server; 2. Try to access with any registry and password not registered; 3. Try to access with registry = "00000000" and passoword = "serverAdminRuUfsc" | Pass: * Displayed the right homepage; * Displayed the rigth navigation menu; Fail: Otherwise; | Any web browser | 2017-04-07
12 |  | Redirecting | Check if the user is redirected to the right home page; Check if the navigation menu is correct for the access level desired; | Victor & Lucas | After loggining in, if the user logged is an admin user (employee): * Check if the page opened displays admin only information; * Check if the navigation menu shows the buttons: "Home", "Manage Credits", "Manage Users" and "View Log"; If user logged in is a student user: * Check if the page opened displays an university restaurant time information and number of people in RU; * Check if the navigation menu shows the buttons: "Home", "Add Credits", "View Log" and "Change Password"; | Pass: * Logged in with the admin user; * Not logged in with any random registry and password; Fail: Otherwise; | Any web browser | 2017-04-07
13 |  | (Employee) Display history (logs) | Check if logs of all users are displayed in the logs screen; | Victor | In the navigation menu, click on the button "View Logs"; | Pass: * Show all the logs stored in database; Fail: Otherwise; | Any web browser | 2017-04-07
14 |  | (Employee) Clear logs | Check if all logs are cleared; | Victor | 1. In the "View Logs" tab, click on the button "Clear log history"; 2. Check if there are any logs in "View Logs"; | Pass: * Only clear log events in "View Logs" tab; Fail: Otherwise; | Any web browser | 2017-04-07
15 |  | (Employee) Filter logs | Check if the textbos is filtering logs correctly by the words typed; | Victor | 1. In the "View Logs" tab, type anything in the "What are you looking for?" box; 2. Check if the text typed is filtering table data; | Pass: * Text typed filtering table data; Fail: Otherwise; | Any web browser | 2017-04-07
16 |  | (Employee) Display students | Check if all students are displayed in the credits screen; | Victor | In the navigation menu, click on the button "Manage credits"; | Pass: * Show students' name, registry number and credits of smartphone and card; Fail: Otherwise; | Any web browser | 2017-04-07
17 |  | (Employee) Filter students | Check if the textbox is filtering students correctly by the words typed; | Victor | 1. In the "Manage Credits" tab, type anything in the "What are you looking for?" box; 2. Check if the text typed is filtering table data; | Pass: * Text typed filtering table data; Fail: Otherwise; | Any web browser | 2017-04-07
18 |  | (Employee) Change credits | Check if the input form of change credits become available when selecting only one user; Check if the event of inserting credit is saved in logs to be resolved by the main board; | Victor | 1. In the "Manage Credits" tab, check any student; 2. Check if it opened a form to input credit data to smartphone and card; 3. Feed some credit; 4. Check if the button to change is only available when user change at least one field; 5. Click on the button and check in "View Log" tab if the event of adding credits has been added; | Pass: * Opened the input form only after selecting a student; * Button only got available after value changing of any credit field; * Created the event of adding credits in logs; Fail: Otherwise; | Any web browser | 2017-04-07
19 |  | (Employee) View users | Check if all users are displayed in the users screen; | Victor | In the navigation menu, click on the button "Manage users"; | Pass: * Show users' name, registry number, tag number, sum of credits of smartphone and card, and access level; Fail: Otherwise; | Any web browser | 2017-04-07
20 |  | (Employee) Fitler users | Check if the textbox is filtering users correctly by the words typed; | Victor | 1. In the "Manage Users" tab, type anything in the "What are you looking for?" box; 2. Check if the text typed is filtering table data; | Pass: * Text typed filtering table data; Fail: Otherwise; | Any web browser | 2017-04-07
21 |  | (Employee) Insert user | Check if the button of insert users become available only when all users are unchecked; Check if the event of clicking the button opens another page to insert user data; Check if new information is loaded in the users page; | Victor | 1. In the "Manage Users" tab, check if the button "Insert user" is olny available when no user is selected; 2. Click on the button "Insert user" and check if it opened a form to feed information of name, registry number, tag number and access level; 3. Click on the button "Save" and check if the new user is loaded in "Manage Users" tab; | Pass: * Insert button only available when no user checked; * After clicking on the button, oppened a form to insert data; * Created the event of new user in logs; * Created the new user and it appeared in "Manage Users" tab; Fail: Otherwise; | Any web browser | 2017-04-07
22 |  | (Employee) Edit user | Check if the button of edit user become available only when a single user is checked; Check if the event of clicking the button opens another page to edit user data; Check if new information is loaded in the users page; | Victor | 1. In the "Manage Users" tab, check if the button "Edit user" is only available when just one user is selected; 2. Click on the button "Edit user" and check if it opened a form to feed information of name, registry number, tag number and access level. Check if the data is pre filled with user to be edited information; 3. Click on the button "Save" and check if the edited user is updated in "Manage Users" tab; | Pass: * Edit button only available when just one user checked; * After clicking on the button, oppened a form to insert data; * The input form has pre filled data of th euser to be edited; * Created the event of updating user in logs; * Uptaded the user and it appeared in "Manage Users" tab; Fail: Otherwise; | Any web browser | 2017-04-07
23 |  | (Employee) Remove user(s) | Check if the button of remove user(s) become available when one or more users are checked; Check if the event of clicking the button removes selected user(s); Check if new information is loaded in the users page; | Victor | 1. In the "Manage Users" tab, check if the button "Delete user(s)" is only available when one or more users are selected; 2. Click on the button "Delete user(s)" and check if the deleted user(s) is/are not displayed in "Manage Users" tab; | Pass: * Delete button only available when one or more users checked; * Created the event of deleting user in logs; * The user does not appear in "Manage users" tab anymore; Fail: Otherwise; | Any web browser | 2017-04-07
24 |  | (Student) Display history (logs) | Check if logs of the student are displayed in the logs screen; | Lucas | In the navigation menu, click on the button "View Logs"; | Pass: * Show only the logs of the student logged in; Fail: Otherwise; | Any web browser | 2017-04-07
25 |  | (Student) Filter logs | Check if the textbos is filtering logs correctly by the words typed; | Lucas | 1. In the "View Logs" tab, type anything in the "What are you looking for?" box; 2. Check if the text typed is filtering table data; | Pass: * Text typed filtering table data; Fail: Otherwise; | Any web browser | 2017-04-07
26 |  | (Student) Add credits | Check if the event of inserting credit is saved in logs to be resolved by the main board; | Lucas | 1. In the "Add credits" tab, feed credits in the input fields; 2. Check if the button to change is only available when user change at least one field; 3. Click on the button and check in "View Log" tab if the event of adding credits has been added; | Pass: * Button only got available after value changing of any credit field; * Created the event of adding credits in logs; Fail: Otherwise; | Any web browser | 2017-04-07
27 |  | (Student) Change password | Check if the button of edit user become available only when a single user is checked; Check if the event of clicking the button opens another page to edit user data; Check if new information is loaded in the users page; | Lucas | 1. In the "Change password" tab, inform you old password and twice your new password in the input fields; 2. Check if the button to change is only available when user change all fields; 3. Click on the button to confirm; 4. Check if you were redirected to login page; 5. Try to login with old password and new password; 6. Check in "View Log" tab if the event of updating user has been added; | Pass: * Button only got available after value changing in all text fields; * Redirected to login page; * Login possible only with new password; * Created the event of updating user in logs; Fail: Otherwise; | Any web browser | 2017-04-07
28 | Board | Communication With App | Check if the board can receive and send messages from/to the app. The app should be seen as a tcp client | Felipe | 1. The app will connect to the board and send a message; 2. The board should wait untill the message arrives; 3. The board will read the message and send it again to the cellphone; 4. The cellphone will receive the message an print it; | Pass: * Message sent pass throught the board and return to the app, beeing printed on the screen; Fail: Otherwise | NodeMCU | 2017-04-07
29 |  | Communication With Server | Check if the board can receive and send messages from/to the server. The board should act as a tcp client | Felipe | 1. The app will connect to the board and send a message; 2. The board should wait untill the message arrives; 3. The board will read the message and send it to the server; 4. The server will receive the message an print it; | Pass: * Message sent passes from the app throught the board and return to the server, beeing printed on the screen; Fail: Otherwise | NodeMCU | 2017-04-07
30 |  | Captcha | Test if a number of five digits could be generated randomically | Felipe | 1. A random number will be generated; 2. The number will be printed second by second | Pass: * The number looks randomic Fail: *The number ramains the same for a long time | NodeMCU | 2017-04-07
31 |  | App response to Captcha Checking | Print an randomic number and wait for the app to connect. When they are connected if the message sended is equal to the randomic number it should return a True boolean, else the user will have to wait for a new captcha. | Felipe | 1. The number is printed on the screen; 2. The App sends a message; 3. If the message is equal return a OK message to the app 4. Else return a not OK message to the app 5. The app print Ok or Not Ok | Pass: * The Ok only is printed on the app when the screen number and the message are the same * Print Ok when the message and the captcha are differente. | NodeMCU | 2017-04-07
32 |  | Get some data from server database | Connect to the server and try to get data from database | Felipe | 1. Connect to server 2. Send an request string to the server 3. Wait for an answer 4. Fill the tree with the data aquired | Pass: * Get Method really receives the right data * The data is corresponds correctly to the request string Fail: * Get data from a random request * Cant connect to the server * Answer takes to long to be transmitted | NodeMCU | 2017-04-07
33 |  | Sincronize board with server | Connect to the server and sync all data the tree have | Felipe | 1. Connect to server 2. Send an request string to the server 3. Wait for an answer 4. Calculate new atomic credits for each student 5. Fill the tree with the data aquired 6. Send atomic data to the server | Pass: *database is the same as the data on the tree; * The atomic credits calculation occurs fine; Fail: Otherwise | NodeMCU | 2017-04-07
34 |  | Test insert method of tree | Insert a Student | Felipe | 1. Insert a Student in a tree 2. Check all its attributes | Pass: * Student inserted * No other student removed * Stuent attributes initialized as expected Fail: Otherwise | NodeMCU | 2017-04-07
35 |  | Test Search method of tree | Search for a student | Felipe | 1. Look for a existing Student in the tree 2. Check its attributes 3. Look for a not existent student in the tree 4. Receive a non existent message | Pass: * Existing Student found * No other student returned * When look for a non existing student receive an error message Fail: Corrupted memory; Otherwise. | NodeMCU | 2017-04-07
36 |  | Test Debit method of tree | Remove Credits from a student | Felipe | 1. Look for an existing student in the tree 2. Check for its credits. 3. If any credit allow student to enter 4. Debit credits | Pass: After enter RU that student credits should be decremented Fail: Otherwise | NodeMCU | 2017-04-07
37 |  | Test tree constructor | Create a tree and check it's root, nodes and height | Felipe | 1. Create a tree 2. Check for all its variables | Pass: *attributes are initialized as expected; Fail: Otherwise | NodeMCU | 2017-04-07
38 |  | Check out of bounds values | Test if a great number of credits is added or for a negative value of credits | Felipe | 1. Search for a student 2. Give him a lot of credits to overflow the variable 3. Receive an error message of value to big 4. If decrementing the credits it should see when the number is zero and stop oing it | Pass: The limits are respected; Fail: Otherwise | NodeMCU | 2017-04-07